## WIP Items
Item | Notes | Responsibility | Timeframe | Status
Review Tracking | Richard to pull together tracking brief for meta and google with tags. Delmon to provide Sirena's details for tracking implementation. | Richard | Medium | Doing
Develop creative for meta ads | Richard to brief in design team for creative assets to serve in meta ads. Creative areas: sales, servicing, and parts. | Richard | Short | Doing
Platform access | Awaiting access to: Instagram for Jessie (see email sent on Saturday). | Delmon | Short | Done
Platform access | Awaiting access to: Google Analytics | Delmon | Short | Done
Platform access | Awaiting access to: Google Tag Manager (ignore for now). |  | Short | On Hold
Build out google ads campaigns | Keywords for new trucks, truck categories/types, servicing, and parts. Richard to share keyword list with Nick for review/approval. | Richard | Short | Doing
Built out meta ads campaigns | Campaign build to be completed once tracking and assets are developed. | Richard | Medium | On Hold
Access to business assets | Rumble to share any brand guidelines, photos, videos, previous reporting and priorities for October to help direct social content. | Nick, Delmon | Short | On Hold
Platform access | Access to meta for Nick to view comments | Richard | Short | Done
October Content Strategy | Plan for content for the month of October. | Jessie | Medium | Doing

## Tracking Brief
Google Ads |  |  | Meta
Tag Name | Tag / Requirement | Instruction | Tag Name | Tag / Requirement | Instruction
Google Tag | <!-- Google tag (gtag.js) --> <script async src="https://www.googletagmanager.com/gtag/js?id=AW-18069786332"></script> <script> window.dataLayer = window.dataLayer ¦¦ []; function gtag(){dataLayer.push(arguments);} gtag('js', new Date()); gtag('config', 'AW-18069786332'); </script> | This is the Google tag for this account. Copy and paste it in the code of every page of your website, immediately after the <head> element. Don't add more than one Google tag to each page | Meta Pixel | <!-- Meta Pixel Code --> <script> !function(f,b,e,v,n,t,s) {if(f.fbq)return;n=f.fbq=function(){n.callMethod? n.callMethod.apply(n,arguments):n.queue.push(arguments)}; if(!f._fbq)f._fbq=n;n.push=n;n.loaded=!0;n.version='2.0'; n.queue=[];t=b.createElement(e);t.async=!0; t.src=v;s=b.getElementsByTagName(e)[0]; s.parentNode.insertBefore(t,s)}(window, document,'script', 'https://connect.facebook.net/en_US/fbevents.js'); fbq('init', '1328602995881864'); fbq('track', 'PageView'); </script> <noscript><img height="1" width="1" style="display:none" src="https://www.facebook.com/tr?id=1328602995881864&ev=PageView&noscript=1" /></noscript> <!-- End Meta Pixel Code --> | 1. Paste base code to website Paste the Meta Pixel code between the <head> and </head> tags of your web page. You may already have other existing code between the head tags, so just place the pixel code underneath that, but above </head>. 2. Refresh your website to save code changes To save and confirm the changes you made to your website's code, refresh your website.
Event Snippet: Submit Lead Form | <!-- Event snippet for Submit lead form conversion page --> <script> gtag('event', 'conversion', {'send_to': 'AW-18069786332/42pLCOeAz5IdENydrKhD'}); </script> | Copy the code below and paste it in between the <head></head> tags of the page(s) you'd like to measure, right after the Google tag. | Meta Lead Event: Submit Lead Form | <script> fbq('track', 'Lead', { lead_type: '{{Enquiry Type}}' }); </script> | Fire the Meta standard Lead event only after the enquiry form has been successfully submitted. Where possible, dynamically populate lead_type with the value selected in the Enquiry Type dropdown, allowing reporting to distinguish between New Truck, Parts, Servicing and other lead types. The event must fire once per successful submission and should not fire from the submit button click alone.
|  |  | Meta Conversions API | Server side Lead event | Implement Meta Conversions API alongside the Meta Pixel. On successful form submission, send the standard Lead event server side. Where possible, include the selected Enquiry Type as lead_type. Pass available customer information permitted by Meta, such as email and phone, to improve Event Match Quality. Ensure appropriate hashing and handling in accordance with Meta requirements and applicable consent/privacy requirements. The browser Pixel Lead event and server CAPI Lead event should use the same event_id so Meta can deduplicate the events and count the lead once.